# Project charter — Plant 2 extrusion line upgrade

Sponsor: Marie-Ève Lacasse, President and CEO

Project lead: Denis Paquette, Director of Operations

Status: Equipment selection complete; awaiting executive sign-off

Capex envelope: $4,200,000 (board approval required)

Version: 1.4 — 2025-11-07

## Objective

Replace the 2009 extrusion line at Plant 2 (Buckingham) with a thermally broken aluminium line, increasing capacity by about 35 % and reducing scrap by 8 points. Commissioning targeted for Q2 2026.

## Governance

Executive steering review with the CEO: Friday, November 14, 2025, 10:00–11:00, Plant 2 conference room (CEO presence required for sign-off of the equipment selection).

Capex request submitted to the Board of Directors at the Q4 meeting of November 20, 2025.

Purchase order to the equipment vendor within 10 days of board approval.

## Risks

Aluminium tariff extension (cost of extrusions).

Vendor lead time of 22 weeks; any delay in sign-off pushes commissioning past Q2 2026.

Downtime at Plant 2 during installation (two weeks, planned during the July shutdown).

## Milestones

| Milestone | Date | Owner | Status |
| --- | --- | --- | --- |
| Vendor shortlist | 2025-10-10 | D. Paquette | Done |
| Final equipment selection | 2025-11-07 | D. Paquette | Done |
| Executive steering review — CEO sign-off | 2025-11-14 10:00 | M.-È. Lacasse | Scheduled |
| Board capex approval | 2025-11-20 | Board | Planned |
| Purchase order issued | 2025-11-28 | Procurement | Planned |
| Commissioning | 2026-05-15 | D. Paquette | Planned |